## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Chưa push được code lên GitHub |  | 1 |  | Closed | Chiến | 2022-05-12 01:20 |  | Iteration 1
Tạo database |  | 2 |  | Closed | Tuấn | 2022-05-13 15:21 |  | Iteration 1
Thêm dữ liệu vào database |  | 3 |  | Closed | Chiến | 2022-05-17 00:34 |  | Iteration 1
Nghiên cứu template html |  | 4 |  | Closed | Nhân | 2022-05-17 00:34 |  | Iteration 1
Template bị config khi đưa vào netbean |  | 5 |  | Closed | Nhân | 2022-05-17 00:34 |  | Iteration 1
Thêm dữ liệu vào database | Database need to add table Guest, Type and Size | 7 |  | Closed | Chiến | 2022-05-17 00:38 |  | Iteration 1
Controller of register | Code controller of register | 8 |  | Closed | Đức | 2022-05-17 01:05 |  | Iteration 1
Login by Gmail accounts |  | 9 |  | Closed | Đức | 2022-05-19 01:02 |  | Iteration 1 | Task | register
Write SRS OverView |  | 10 |  | Closed | Tuấn | 2022-05-26 00:51 |  | Iteration 1 | Task
Forgot Pass word |  | 11 |  | Closed | Đức | 2022-05-26 00:51 |  | Iteration 1
Search and sort TV |  | 12 |  | Closed | Chiến | 2022-05-26 00:51 |  | Iteration 2 | Task | Home
Home Page vẫn đang fix cứng | Push real data to home page | 13 |  | Closed | Chiến | 2022-05-28 09:44 |  | Iteration 2 | Task | Home
Phân trang search TV vẫn chưa chuẩn |  | 14 |  | Closed | Nhân | 2022-05-28 11:38 |  | Iteration 2
Làm tiếp Add to cart của customer |  | 15 |  | Closed | Chiến | 2022-05-28 11:39 |  | Iteration 2
Write SRS Functional Requirements |  | 16 |  | Doing | Tuấn | 2022-05-28 11:39 |  | Iteration 2
Edit SRS OverView | change symbol "..." into etc, fix Screen flow | 17 |  | Closed | Tuấn | 2022-05-28 11:39 |  | Iteration 2
Edit SDS OverView | Finding about sequence diagram | 18 |  | Doing | Tuấn | 2022-05-28 11:39 |  | Iteration 3
Export order to excel | Finding to export order to excel function | 19