## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in and sign up. | Nhân | Done | II.2 | II.3 | Finding and Code Template
2 | User Login | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | II.1 | II.1
3 | User Register | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | II.1 | II.2
4 | Forgot Password | Common | This is screen which allows the user to enter email then when user submit, user can receive a email to have user know system reset user's password to a random | Đức | Done | II.5
6 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in, sign up and search product. | Chiến | Done | II.2 | II.3 | Add list products by model to HomePage function
7 | User Login | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | To Do | II.1 | II.1 | Add Login with Google account function
8 | Search Product | Common | A screen can display list of all televisons user searching | Chiến | To Do
9 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in, sign up and search product. | Nhân | Done | II.2 | II.3 | Add pagination function
10 | Search Product | Common | A screen can display list of all televisons user searching | Nhân | To Do |  |  | Add pagination function
11 | Profile | Common | This is a screen which allows the user to view, change and update new information of profile. In this page, user update FirstName, Lastname, Email, Phone, Address, Gender, D.O.B, Avatar. | Nhân | To Do

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in and sign up. | Nhân | Done | II.2 | II.3 | Finding and Code Template
2 | User Login | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | II.1 | II.1
3 | User Register | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | II.1 | II.2
4 | Forgot Password | Common | This is screen which allows the user to enter email then when user submit, user can receive a email to have user know system reset user's password to a random | Đức | Done | II.5
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in, sign up and search product. | Chiến | Done | II.2 | II.3 | Add list products by model to HomePage function
2 | User Login | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | To Do | II.1 | II.1 | Add Login with Google account function
3 | Search Product | Common | A screen can display list of all televisons user searching | Chiến | To Do
4 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in, sign up and search product. | Nhân | Done | II.2 | II.3 | Add pagination function
5 | Search Product | Common | A screen can display list of all televisons user searching | Nhân | To Do |  |  | Add pagination function
6 | Profile | Common | This is a screen which allows the user to view, change and update new information of profile. In this page, user update FirstName, Lastname, Email, Phone, Address, Gender, D.O.B, Avatar. | Nhân | To Do
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Add to Cart | Common | This is short descripiton for the screen/function (2-3 sentences) | Chiến | Done
2 | Product Manage | Common | This is screen which allows Import staff to edit price, amount, add new televison in to warehouse | Nhân | Done
3 | User Manage | Common | This is screen which allows Admin to edit user in to database | Đức | Done
4 | Product Manage | Common | This is screen which allows Import staff to edit price, amount, add new televison in to warehouse | Nhân | Done
5 | Add to Cart | Common | This is screen which allows User View price, amount of total choosen product and buy | Chiến | Done
6 | Write feedback | Common | This is screen which allows User bought product can write feedback | Đức | Done
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document