## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Chưa push được code lên GitHub |  | 1 |  | Closed | Chiến | 2022-05-12 01:20 | 2023-12-01 | Iteration 1 | Task
Tạo database |  | 2 |  | Closed | Tuấn | 2022-05-13 15:21 | 2023-12-01 | Iteration 1 | Task
Thêm dữ liệu vào database |  | 3 |  | Closed | Chiến | 2022-05-17 00:34 | 2023-12-01 | Iteration 1 | Task
Nghiên cứu template html |  | 4 |  | Closed | Nhân | 2022-05-17 00:34 | 2023-12-01 | Iteration 1 | Task
Template bị config khi đưa vào netbean |  | 5 |  | Closed | Nhân | 2022-05-17 00:34 | 2023-03-02 | Iteration 1 | Task
Thêm dữ liệu vào database | Database vẫn chưa hoàn chỉnh phải thêm bảng Guest, Type và Size | 6 |  | Closed | Chiến | 2022-05-17 00:38 | 2023-03-02 | Iteration 1 | Task
Controller of register | triển khai code controll của screen của register | 7 |  | Closed | Đức | 2022-05-17 01:05 | 2023-10-02 | Iteration 1 | Task
Login by Gmail accounts |  | 8 |  | Closed | Đức | 2022-05-19 01:02 | 2023-10-02 | Iteration 1 | Task | register
Write SRS OverView |  | 9 |  | Closed | Tuấn | 2022-05-26 00:51 | 2023-10-02 | Iteration 1 | Task
Forgot Pass word |  | 10 |  | Closed | Đức | 2022-05-26 00:51 | 2023-10-02 | Iteration 1 | Task | Forgot password
Search and sort TV |  | 11 |  | Closed | Chiến | 2022-05-26 00:51 | 31/01/2023 | Iteration 2 | Task | Home
Home Page vẫn đang fix cứng | Cần đẩy được dữ liệu lên home page | 12 |  | Closed | Chiến | 2022-05-28 09:44 | 31/01/2023 | Iteration 2 | Task | Home
Phân trang search TV vẫn chưa chuẩn |  | 13 |  | Closed | Nhân | 2022-05-28 11:38 | 2023-03-02 | Iteration 2 | Task | Search product
Làm tiếp CRUD của customer |  | 14 |  | Closed | Đức | 2022-05-28 11:39 | 2023-03-02 | Iteration 2 | Task
Write SRS Functional Requirements |  | 15 |  | Closed | Tuấn | 2022-05-28 11:39 | 2023-07-02 | Iteration 2 | Task
Edit SRS OverView | Đổi ký tự "..." thảnh etc, sửa Screen flow gần nhau, dễ nhìn hơn | 16 |  | Closed | Tuấn | 2022-05-28 11:39 | 2023-07-02 | Iteration 2 | Task
Edit SRS OverView | Đổi ký tự "..." thảnh etc, sửa Screen flow gần nhau, dễ nhìn hơn | 17 |  | Closed | Tuấn | 2022-05-28 11:39 | 2023-10-02 | Iteration 2 | Task
Edit front end | Chỉnh phần "about us" bé lại | 18 |  | Closed | Nhân | 2022-05-28 11:39 | 14/02/2023 | Iteration 3 | Task | Change password
Edit font Thank you after buy product | Đổi sang tiếng việt | 19 |  | Closed | Chiến | 2022-05-28 11:39 | 17/02/2023 | Iteration 3 | Task | Thank you
Edit Change pass word function | thêm popup message nếu đổi mật khẩu thành công | 20 |  | Closed | Đức | 2022-05-28 11:39 | 21/02/2023 | Iteration 3 | Task | Change password
Edit font text | Đổi hết trang thành tiếng việt có dấu | 21 |  | Closed | Nhân | 2022-05-28 11:39 | 28/02/2023 | Iteration 4 | Task
Edit price | xóa kí hiệu đ sau giá của sản phẩm | 22 |  | Closed | Chiến | 2022-05-29 11:39 | 2023-03-03 | Iteration 4 | Task | Product detail
Edit SDS Sequence diagram | Sửa lại sequence diagram | 23 |  | Closed | Tuấn | 2022-05-30 11:39 | 2023-03-03 | Iteration 4 | Task
Edit Thank you after buy product | Đổi không để thành trang có từ Cam on | 24 |  | Closed | Chiến | 2022-05-31 11:39 | 2023-03-03 | Iteration 4 | Task | Thank you
Edit Manage user | Admin chỉ sửa thông tin của nhân viên còn khách hàng thì block hoặc unblock | 25 |  | Closed | Chiến | 2022-06-01 11:39 | 2023-11-03 | Iteration 4 | Task | Manage user