## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Customer | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in and sign up. | Nhân | Done | iter1 | iter2 | Add pagination function
2 | User Login | Admin | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | iter1 | iter2 | Add Login with Google account function
3 | User Register | User | This is screen which allows the user to register. | Đức | Done | iter1 | iter1
4 | Forgot Password | User | This is screen which allows the user to enter email then when user submit, user can receive a email to have user know system reset user's password to a random | Đức | Done | iter1 | iter1
5 | Search Product | Customer | A screen can display list of all televisons user searching | Chiến | Done | iter2 | iter2
6 | User Profile | User | This is a screen which allows the user to view, change and update new information of profile. In this page, user update FirstName, Lastname, Email, Phone, Address, Gender, D.O.B, Avatar. | Nhân | Done | iter2 | iter2
7 | User Manage | Admin | This is screen which will display list of user to manage, Admin can edit, add new staff and block customer | Đức | Done | iter3 | iter3
8 | Product Manage | Inprort staff | This is screen which will display list of user to manage, Admin can edit, add new staff and block customer | Nhân | Done | iter3 | iter3
9 | Add to Cart | Customer | This function will add choosen product into cart of customer | Chiến | Done | iter3 | iter3
10 | Edit product | Inprort staff | This screen will allow Import staff to edit choosen product | Nhân | Done | iter3 | iter3
11 | Edit Account | Admin | this function let Admin to edit account If role of edit account is customer => allow to change status block, unblock. If role of edit account is staff => allow to edit account. | Đức | Done | iter4 | iter4
12 | Add Staff Account | Admin | This is function which allows Admin to add staff | Đức | Done | iter4 | iter4
13 | Delete staff account | Admin | This is function allows Admin to delete staff | Đức | Done | iter4 | iter4
14 | Add Product | Inprort staff | This is function allows Import staff to add new product | Nhân | Done | iter4 | iter4
15 | Edit cart | Customer | This is function allows customer to edit cart | Chiến | Done | iter4 | iter4
16 | Tracking order | Customer | This screen allows admin to tranking order | Chiến | Done | iter4 | iter4
17 | Manage revenue | Admin | This screen display revenue information for Admin | Đức | Done | iter5 | iter5
18 | Export order to excel | Admin | This function allows admin to export order to excel and download it | Đức | Done | iter5 | iter5
19 | Manage order | Payment Staff | This function allows payment staff to manage order | Nhân | Done | iter5 | iter5
20 | Update order | Payment Staff | This function allows payment staff to update order | Nhân | Done | iter5 | iter5
21 | Search order | Payment Staff | This function allows payment staff to search order | Nhân | Done | iter5 | iter5
22 | Purchase | Customer | This function allows user and customer to buy product. anh send list of product to database | Chiến | Done | iter5 | iter5

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in and sign up. | Nhân | Done | II.2 | II.3 | Finding and Code Template
2 | User Login | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | II.1 | II.1
3 | User Register | Common | This is screen which allows the user to register. | Đức | Done | II.1 | II.2
4 | Forgot Password | Common | This is screen which allows the user to enter email then when user submit, user can receive a email to have user know system reset user's password to a random | Đức | Done | II.5 | II.8
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in, sign up and search product. | Chiến | Done | II.2 | II.3 | Add list products by model to HomePage function
2 | User Login | Common | This is screen which allows the user to enter email or username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it. | Đức | Done | II.1 | II.1 | Add Login with Google account function
3 | Search Product | Customer | A screen can display list of all televisons user searching | Chiến | Done | II.16 | II.17
4 | Home Page | Common | HomePage to view many kind of television by model. On this screen have link for user to add to cart, sign in, sign up and search product. | Nhân | Done | II.2 | II.3 | Add pagination function
5 | Search Product | Customer | A screen can display list of all televisons user searching | Nhân | Done | II.16 | II.17 | Add pagination function
6 | User Profile | Common | This is a screen which allows the user to view, change and update new information of profile. In this page, user update FirstName, Lastname, Email, Phone, Address, Gender, D.O.B, Avatar. | Nhân | Done | II.4 | II.5
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Product Manage | Import Staff | This is screen will display list of product to manage, Imprort staff can edit, add new product | Nhân | Done | II.12 | II.13
2 | User Manage | Admin | This is screen display list of user for Admin to manage | Đức | Done | II.7 | II.9
3 | Add to Cart | Customer | This function will add choosen product into cart of customer | Chiến | Done | II.20 | II.14
4 | Edit product | Improt Staff | This screen will allow Import staff to edit choosen product | Nhân | Done | II.14 | II.15
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Edit Account | Admin | this function let Admin to edit account If role of edit account is customer => allow to change status block, unblock. If role of edit account is staff => allow to edit account. | Đức | Done | II.3 | II.5
2 | Add Staff Account | Admin | This is function which allows Admin to add staff | Đức | Done | II.8 | II.10
3 | Delete staff account | Admin | This is function allows Admin to delete staff | Đức | Done | II.9 | II.11
4 | Add Product | Import Staff | This is function allows Import staff to add new product | Nhân | Done | II.13 | II.14
5 | Edit cart | Customer | This is function allows customer to edit cart | Chiến | Done | II.21 | II.21
6 | Tracking order | Customer | This screen allows admin to tranking order | Chiến | Done | II.23 | II.23
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter5
Iteration Tracking - Iteration 5
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Manage revenue | Admin | This screen display revenue information for Admin | Đức | Done | II.10 | II.24
2 | Export order to excel | Admin | This function allows admin to export order to excel and download it | Đức | Done | II.11 | II.12
3 | Manage order | Payment Staff | This function allows payment staff to manage order | Nhân | Done | II.17 | II.17
4 | Update order | Payment Staff | This function allows payment staff to update order | Nhân | Done | II.18 | II.18
5 | Search order | Payment Staff | This function allows payment staff to search order | Nhân | Done | II.19 | II.19
6 | Purchase | Customer | This function allows user and customer to buy product. anh send list of product to database | Chiến | Done | II.22 | II.22
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document